Work programme

Official starting date: 1 August 2010

Official end date: 31 July 2012

| Date | Activities |
| --- | --- |
| September 2010 | Partners agreement on date and agenda of the first transnational meeting in Spain. Organisations choose the family carers learners. First partnership internal newsletter. |
| October 2010 | National meetings N.1 Presentation of the partnership. Preparation of methodology at national level. |
| November 2010 | Transnational meeting N.1 - Spain Presentation of the partnership and partners: objectives, roles and responsibilities. Formalisation of methodologies for work, assessment and dissemination. Presentation of the Spanish situation, exchanges between family carers and with professionals. Presentation of the common framework for analysis of the obstacles to family carers’ perception and self-assessment of their needs (questionnaire prepared by CEAFA and CWSP). Discussion |
| November 2010- February 2011 | In each country, dissemination of the questionnaire on obstacles, collection of responses and first analysis |
| February 2011 | National meetings N.2 Finalization of results of the national surveys on obstacles. |
| March 2011 | Transnational meeting N.2 - Belgium Review of results of the national surveys on obstacles. Discussion. Methodology for the collection of existing tools to help self-assessment, and of good practices. Presentation of the common framework for analysis of conditions for family carers’ take-up of the needs assessment and formulation tools, and the impact of these tools on relations between family carers and professionals (questionnaire prepared by APF and CWSP). Discussion. Presentation of the Belgian situation, exchanges between family carers and with professionals. |
| April 2011 | Delivery by CEAFA of a summary report on obstacles to the perception and self-assessment of their needs by family carers, based on the results of national surveys and of the meeting in Belgium. |
| March 2011- May 2011 | In each country, dissemination of the questionnaire on tools and their impact, collection of responses and first analysis. |
| May 2011 | National meetings N.3 Finalization of results of the national surveys on tools and their impact. Identification of best practices. |
| Mai 2011 | Transnational meeting N.3 - Cyprus Review of results of the national surveys on tools and their impact and best practices. Determination of the first trends. Presentation of the situation in Cyprus, exchanges between family carers and with professionals. Presentation of the interim evaluation report and review of the project according to its conclusions. |
| June 2011 | Delivery of interim reports to national agencies by all official partners. |
| June 2011 | Delivery by APEMH CWSP of draft recommendations on training provision to be made for family carers or professionals to help family carers assess and express their needs. |
| September 2011 | National meetings N.4 Finalization of the identification of good practices. Work on the draft recommendations on training provision to be made for family carers or professionals to help family carers assess and express their needs. |
| October 2011 | Transnational meeting N.4 - France Finalization of the analysis of tools, best practices collected, and trends. Work on the draft recommendations for training provision. Presentation of the French situation, exchanges between family carers and with professionals. |
| November 2011 | Delivery by the Carers Association and CWSP of draft common recommendations for the future design of new tools for self-assessment and formulation of needs by family carers. |
| January 2012 | National meetings N.5 Finalization of the work on the recommendations on training provision to be made for family carers or professionals to help family carers assess and express their needs. Work the draft recommendations for the design of tools. |
| February 2012 | Transnational meeting N.5 - Slovakia Finalization of the recommendations on training. Work on the recommendations on tools. Presentation of the Slovak situation, exchanges between family carers and with professionals. |
| March 2012 | National meetings N.6 Finalization of the full set of recommendations (training + tools). Discussion concerning the legacy of the project. |
| April 2012 | Finalization (content + lay out) of the full set of recommendations (including best practices examples). Circulation of proposals for the project legacy. |
| May 2012 | Transnational meeting N.6 - Ireland Discussion on potential for sustaining project network beyond the formal end date of the project. Presentation of the European recommendations. Discussion on final dissemination plans. Dissemination event organized by the host partner (including presentation of the Irish situation). |
| June 2012 | Dissemination activities at local, regional and national level. Promotion at EU level with the cooperation of EU NGOs (COFACE, Eurocarers, ...). . |
| July 2012 | Continuation of dissemination activities at local, regional and national level. Delivery of the project final evaluation report. Formal end of the project. |
| September 2012 | Delivery of final reports to national agencies by all official partners. Possible continuation of the project network through other initiatives (joint work within EU NGOs, new projects, ...) in order to implement the recommendations. |